## Strategic Plan Actions Tracker
Pillar | Action ID | Launch Date | Status | Action | Cabinet Lead 1 | Cabinet Lead 2 | Project Lead 1 | Project Lead 2 | Project Lead 3 | Initial Plan Review Date | Initial Plan Approval Date | Date for Next Plan Quarterly Review | Editable Action Plan Link | Modified | Modified By
Pillar 1 | P1.F2.A1 | 2025-07-01 | In Progress | Implement the Golden LEAF Schools Initiative through cross-agency collaboration to transform educator practice and student outcomes in rural schools, focusing on high-quality mathematics instruction via the High Reliability Schools model. | Maria Pitre-Martin |  | Rachel Wright-Junio |  |  | 2025-12-19 |  |  |  | 2026-01-06 16:07 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F4.A1 | 2025-08-01 | In Progress | Promote awareness of NC College Connect, NextNC and the NC Need Based Scholarship to provide direct admission to North Carolina colleges and universities and financial aid to support the cost of attendance. | Stacey Wilson-Norman |  | Sneha Shah-Coltrane |  |  | 2026-01-30 | 2026-01-30 |  | https://docs.google.com/document/d/1E3-9DaZ8JUm_fucyz_UJ2wLnwQsWrtMyVnqc-3Nh-Q0/edit?tab=t.0 | 2026-02-02 09:49 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F2.A1 | 2025-08-01 | In Progress | Advocate for continued expansion of the Advanced Teaching Roles program. | Geoff Coltrane | Derrick Jordan | Tom Tomberlin | Charlene Pittman | Leah Sutton | 2026-01-28 | 2026-01-28 |  | https://docs.google.com/document/d/1LYwzRy1rJ0T5gDwWE0cEOO1NLB9cRi0alXN7__NRdgs/edit?tab=t.0 | 2026-02-12 17:22 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F3.A1 | 2025-08-01 | In Progress | Implement with limited challenges the student information system, NCSIS powered by Infinite Campus. | Vanessa Wrenn |  | Sri Viswanathan | Rob Dietrich | Matthew Mayo | 2025-12-19 |  |  |  | 2026-01-06 16:07 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F1.A1 | 2025-09-01 | In Progress | Strengthen physical security measures in PSUs, such as perimeter control, secured access points and protected internal spaces, through school construction assistance provided by NCDPI. | Derrick Jordan |  | Nathan Maune |  |  | 2026-01-30 | 2026-01-30 |  | https://docs.google.com/document/d/1Kr17--rOeTzav-SzopXYBgL2oVEExTacG3UWUW4EefA/edit?tab=t.0 | 2026-02-12 17:22 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F4.A1 | 2025-10-01 | In Progress | Establish an SBE Task Force to develop a new school-level accountability system that will: Consider the variability among high schools with respect to available opportunities and funding, such as Advanced Placement, CTE courses, etc.; Reliably assess multiple measures of student performance in grades 3-12 that includes measures of progress towards ensuring all students graduate prepared for their next phase of life | Rupen Fofaria | Michael Maher | Curtis Sonneman |  |  | 2025-09-30 | 2025-09-30 |  | https://docs.google.com/document/d/1n7S4mMG0cXbBIEzUF8V-QToOfeR6Y4YUVkiQbsO1Wkw/edit?tab=t.0 | 2025-11-21 14:47 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F1.A1 | 2025-10-01 | In Progress | Use research and assessment of current NCDPI partners’ initiatives and messaging for public education. | Mark Dessauer |  |  |  |  | 2025-10-14 | 2025-10-14 |  | https://dpincgov-my.sharepoint.com/:w:/g/personal/mark_dessauer_dpi_nc_gov/EUDl6VtFr5tMq23foJ4TBrEBtheDu11xEz8U8Jj6zFxF8A?e=c9a21m | 2025-11-21 15:49 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F2.A1 | 2025-12-01 | In Progress | Engage, align and support PSU communications staff to align communication efforts that celebrate public education. | Mark Dessauer |  | Jeanie McDowell |  |  | 2025-10-21 | 2025-10-21 |  | https://dpincgov-my.sharepoint.com/:w:/r/personal/mark_dessauer_dpi_nc_gov/Documents/Comms%20NCDPI/Workplans/Pillar%207/P7.F2.A1_StrategicPlan_ProjectPlan_PIOEngagement_10_20_2025.docx?d=wa6990dd5e0504284b01cc1e3d1a0425b&csf=1&web=1&e=e0pvRq | 2025-12-02 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F3.A1 | 2025-12-01 | In Progress | Work with education partners on statewide communication efforts that uplift success stories, testimonials and positive narratives about public schools. | Mark Dessauer |  |  |  |  | 2025-10-28 | 2025-10-28 |  | https://docs.google.com/document/d/1MOg2y3SdgDcpLgRvyYSV843ZreejK-jtooBn4tW98eA/edit?usp=sharing | 2025-12-02 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F1.A1 | 2026-01-01 | In Progress | Expand high-quality pre-K and strengthen kindergarten readiness by partnering with North Carolina Department of Health and Human Services (NCDHHS) and PSUs to align standards, coordinate inclusive early learning systems and enhance transition supports. | Stacey Wilson-Norman |  | Dan Tetrault |  |  | 2025-10-21 | 2025-12-16 |  | https://docs.google.com/document/d/1j6MlhsEcoJRd4x8u0qgcX-KFqJnvOCOL3gXSJNE3W4w/edit?tab=t.0 | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F4.A2 | 2026-01-01 | In Progress | Provide PSUs with technical assistance to implement Career Development Plans so that students graduate with a purposeful plan for their future. | Stacey Wilson-Norman |  | Trey Michael | Kristi Day |  | 2025-11-07 | 2025-11-07 |  | https://docs.google.com/document/d/1FbGe42kjM0DeR3vbeJdln6mQw7nRgnvo_XvYZfsAt3g/edit?tab=t.0 | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F1.A1 | 2026-01-01 | In Progress | Identify ways to develop translations of NCDPI resources based on student demographics. | Mark Dessauer |  | Corrie Byrd |  |  | 2025-11-25 | 2025-11-25 |  | https://docs.google.com/document/d/1ZW0cbsP7j1HXsDyI_w1Hp9n1QMqFsq1cnZuh0n3BCx0/edit?usp=sharing | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F1.A2 | 2026-01-01 | In Progress | Support PSUs in creating safe and secure online learning environments by providing tools, best practices and advanced training for educators on virtual classrooms and secure online interactions. | Vanessa Wrenn |  | Matthew Mayo | Ashley McBride |  | 2025-11-14 | 2025-11-14 |  | https://docs.google.com/document/d/1GGNYyzche9BqR825X_nAHfUmx8SxAEj50l0m7kOK1fs/edit?usp=sharing | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F2.A1 | 2026-01-01 | In Progress | Guide PSUs in identifying and applying best practices to limit distractions from wireless devices and promote responsible social media use to support safe and focused learning environments. | Vanessa Wrenn |  | Matthew Mayo | Ashley McBride |  | 2025-11-07 | 2025-11-07 |  | https://docs.google.com/document/d/17ncfStwwDxxO52p1k-MBGMrA0KWVTxxYwfEiIJG-hls/edit?tab=t.0 | 2026-01-29 17:11 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F2.A2 | 2026-01-01 | In Progress | Identify and share effective practices for reducing chronic absenteeism and strengthening student attendance. | Michael Maher |  | Shaun Kellogg |  |  | 2025-12-02 | 2025-12-02 |  | https://docs.google.com/document/d/1bydWE2KF8_ru4XmRRD8gHkYUxs0CY1bCOJ38SJBiIWw/edit?tab=t.0 | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F1.A1 | 2026-01-01 | In Progress | Implement an agencywide language access plan and ensure communications and website materials meet accessibility standards to better serve diverse PSU needs. | Mark Dessauer |  | Corrie Byrd | Eric Knuckles |  | 2025-11-25 | 2025-12-02 |  | https://docs.google.com/document/d/14-sRmTNgNcnRi1BVLBMJxvZ_BQmv6uWsHrB36Qv1fx4/edit?usp=sharing | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F2.A1 | 2026-01-01 | In Progress | Establish an intra-agency working group to identify and address barriers to operational consistency, collaboration and communication across NCDPI offices. | Maria Pitre-Martin |  | Jeani Rousseau |  |  | 2025-11-14 | 2025-11-14 |  | https://docs.google.com/document/d/1iOx9Cd2pDzBa6DvQk_Ffx6u8NaMYyCZxFppZbj2ODho/edit?tab=t.0 | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F2.A2 | 2026-01-01 | In Progress | Reestablish the NCDPI Agency Roundtable to monitor collaboration and communication with PSUs. | Stacey Wilson-Norman |  | Monique Felder |  |  | 2025-11-07 | 2025-11-07 |  | https://docs.google.com/document/d/1sD8rpoVwjv3dcYfe3Z0csVmpshYz_A0SLPVi2-CoeAo/edit?tab=t.0 | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F1.A1 | 2026-01-01 | In Progress | Create a cross-sector Innovation Leadership Council (charter, district and lab school leaders, along with NCDPI staff) to guide knowledge transfer and scale-up. | Michael Maher | Maria Pitre-Martin | Shaun Kellogg |  |  | 2025-12-02 | 2025-12-02 |  | https://docs.google.com/document/d/12Y5iBG19iTSF34PuQ-qjlVZYYJeJ7k1jvvxUusHYMRI/edit?tab=t.0 | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F4.A2 | 2026-01-01 | In Progress | Enhance interim assessments aligned to the North Carolina Standard Course of Study, promote multiple measures beyond standardized assessments and provide PSUs with the resources to increase progress monitoring using assessment data. | Michael Maher |  | Kinge Mbella | Kristi Day |  | 2025-10-28 | 2025-10-28 |  | https://docs.google.com/document/d/1MUCKK2vD-P-sYloG9hzLOpDnaaodk5G_5gAmsGGU0wc/edit?usp=sharing | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F1.A2 | 2026-01-01 | In Progress | Work with partners to develop and test comprehensive public education messaging. | Mark Dessauer |  |  |  |  | 2025-11-14 | 2025-11-25 |  | https://docs.google.com/document/d/1h6g4bfPovQKVgqTj47r3WUAdRlJgY5wGU02bHIISh-g/edit?usp=sharing | 2026-01-27 17:42 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F2.A1 | 2026-01-01 | Not Started | Develop and launch a statewide reading campaign, such that students will collectively read 10 million books annually, in collaboration with state and local partners. | Mark Dessauer | Vanessa Wrenn | Sabrina Steigelman | Tonia Parrish | Molly McGowan Gorsuch | 2026-03-03 | 2026-03-17 |  | https://docs.google.com/document/d/1bv6i_DNV_bW1CN6ykZHCWgqwIBjWdtClOUgKJZVKPEM/edit?usp=sharing | 2026-03-28 18:49 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F2.A2 | 2026-02-01 | In Progress | Strengthen digital learning and literacy pre-K-12 by developing high-quality, standards-aligned online content, formalizing NCDPI’s approach to supporting PSUs with goals and a data-driven framework for effective digital and personalized learning environments and continuing to guide the responsible use of artificial intelligence. | Vanessa Wrenn |  | Matthew Mayo | Vera Cubero | Heather Pennica | 2026-01-13 | 2026-01-27 |  | https://docs.google.com/document/d/1_f2EpzGMbg95YjYT0-t1BrrRaQ-GW7WRJQui2cVvia4/edit?tab=t.0 | 2026-02-12 17:22 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F2.A2 | 2026-02-01 | In Progress | Establish an SBE task force to develop: a licensure model that is more transparent and includes multiple pathways into the profession; an updated online licensure system that is user-friendly and guides applicants through the application process; apprenticeship models; pathways for professional advancement, such as exploring mentoring or coaching opportunities and additional local or state financial incentives for serving in advanced roles or high-need schools; and valid and reliable measures of teacher impact and effectiveness | Rupen Fofaria | Derrick Jordan |  |  |  | 2026-01-20 | 2026-01-27 |  | https://docs.google.com/document/d/1Sh6U1jPyAtNVPtIrepc2b7zQ4AeaxtOynksaxo46U3U/edit?tab=t.0 | 2026-02-12 17:22 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F2.A3 | 2026-02-01 | Not Started | Create key performance indicators for all NCDPI offices aligned to the strategic plan to monitor and drive agency effectiveness. | Maria Pitre-Martin |  |  |  |  | 2026-01-27 |  |  |  | 2026-01-13 17:54 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F3.A1 | 2026-02-01 | In Progress | Explore redesign of the statutory process for identifying low-performing schools to ensure it is supportive, research-informed and better aligned to improvement needs. | Michael Maher | Stacey Wilson-Norman | Curtis Sonneman | Alex Charles | Monique Felder | 2026-02-10 | 2026-02-10 |  | https://docs.google.com/document/d/1n7S4mMG0cXbBIEzUF8V-QToOfeR6Y4YUVkiQbsO1Wkw/edit?tab=t.0 | 2026-02-12 17:22 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F1.A2 | 2026-03-01 | Not Started | Conduct a comprehensive needs assessment of parent and community resources at NCDPI (personnel, funds, training, instruments, current activities, etc.). | Maria Pitre-Martin | Stacey Wilson-Norman |  |  |  | 2026-02-24 |  |  |  | 2026-02-12 17:22 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F1.A3 | 2026-03-01 | Not Started | Form an advisory group to play a role in needs identification, decision making and plans to enhance parent, family and community engagement. | Rupen Fofaria |  |  |  |  | 2026-03-03 | 2026-03-10 |  | https://docs.google.com/document/d/1SWmUK-gz6Jv3DAlk3Dc0cNgSadCW-R8c_wqSfTEhoac/edit?tab=t.0 | 2026-03-13 10:53 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F2.A3 | 2026-03-01 | Not Started | Promote student and staff well-being by supporting PSUs in implementing Whole School, Whole Community, Whole Child models to foster positive school climates and elevate student voice and belonging. | Stacey Wilson-Norman | Rupen Fofaria | Kristi Day | Ellen Essick |  | 2026-01-27 | 2026-02-03 |  | https://docs.google.com/document/d/1xydckQUwQiTPXa2YAXdCMed034pehKU1dmMBOV4PPAo/edit?tab=t.0 | 2026-02-05 17:37 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F3.A2 | 2026-03-01 | Not Started | Develop and implement a centralized data governance framework to promote the standardization of data collection, validation, definition and reporting processes across all NCDPI departments. | Vanessa Wrenn |  | Rob Dietrich | Sri Viswanathan | Amy Powell Moman | 2026-02-17 | 2026-02-17 |  | https://docs.google.com/document/d/1Y3tStMrddVFp5cTvOoyYJcazrBOQpcGM8f3oKnd8nIQ/edit?tab=t.0 | 2026-03-17 10:11 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F1.A2 | 2026-03-01 | Not Started | Establish a structured process to identify, pilot, evaluate and/or scale innovative school models and instructional practices across North Carolina. | Michael Maher |  | Shaun Kellogg |  |  | 2025-12-02 | 2025-12-02 |  | https://docs.google.com/document/d/12Y5iBG19iTSF34PuQ-qjlVZYYJeJ7k1jvvxUusHYMRI/edit?tab=t.0 | 2025-12-02 17:25 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F1.A3 | 2026-03-01 | Not Started | Create accessible and engaging materials about how public education works and is managed in North Carolina. | Mark Dessauer |  |  |  |  | 2026-02-03 | 2026-02-10 |  | https://docs.google.com/document/d/1tvWY8f4BuVmbyupNIr8WkiGDMLdf4tz5zfHG13j-sgQ/edit?tab=t.0 | 2026-02-10 15:58 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F2.A2 | 2026-03-01 | Not Started | Engage, connect and support NCDPI staff and education partners to align communication efforts that celebrate public education. | Mark Dessauer |  |  |  |  | 2026-02-03 | 2026-02-17 |  | https://docs.google.com/document/d/1qL329xlmrwJd0CvzKdRADrOezOHcVhUzqMP86HO7g20/edit?tab=t.0 | 2026-03-13 11:04 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F3.A2 | 2026-03-01 | Not Started | Coordinate and share messaging that celebrates public education successes. | Mark Dessauer |  |  |  |  | 2026-02-10 | 2026-02-17 |  | https://docs.google.com/document/d/1jcsTxPYQkbj2APZbxdyTK0O_0_VOJrx3Y7-2K1pqgFg/edit?tab=t.0 | 2026-03-13 11:04 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F3.A1 | 2026-04-01 | Not Started | Support PSUs in expanding access to rigorous pathways, such as AP, International Baccalaureate (IB), Cambridge International, Career and College Promise (CCP), credentialed Career and Technical Education (CTE) and Junior Reserve Officers’ Training Corps (JROTC), to ensure every student takes and passes a college level and career-connected course. | Stacey Wilson-Norman |  | Sneha Shah Coltrane | Trey Michael |  | 2026-03-17 | 2026-03-17 |  | https://docs.google.com/document/d/1z-XOlBO3ejx1t2publAr7dywWgW3TMEdn2ygJsgLuk0/edit?tab=t.0 | 2026-03-28 18:46 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F1.A4 | 2026-05-01 | Not Started | Create supportive materials and training for PIOs and NCDPI partners to adopt and adapt and coordinate communications. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F3.A3 | 2026-05-01 | Not Started | Encourage the number of joint events and community engagement activities where NCDPI and education partners present unified messaging about public education. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F1.A1 | 2026-05-01 | Not Started | Engage and train partners and communicators to advocate for public education. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F1.A4 | 2026-06-01 | Not Started | Promote collaboration and partner with PSUs to share best practices on effective communication between schools and families. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F2.A1 | 2026-06-01 | Not Started | Engage philanthropic and business communities to fund and support research and adoption of innovative reform models. | Mark Dessauer | Michael Maher | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F1.A2 | 2026-06-01 | Not Started | Improve ability of PSU staff to communicate with NCDPI by making contact information more accessible and transparent and by enhancing support protocols, such as regular NCDPI staff office hour sessions. | Maria Pitre-Martin | Vanessa Wrenn | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F1.A3 | 2026-06-01 | Not Started | Develop and administer a survey to central office staff (a “DPI Customer Service Survey”) to assess customer service strengths and needs. | Maria Pitre-Martin |  |  |  |  | 2026-03-10 |  |  |  | 2026-03-10 15:24 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F1.A4 | 2026-06-01 | Not Started | Create and share NCDPI guidance focused on capacity building for PSUs, including best practices for strategic purchasing decisions and aligning budget decisions with instructional priorities. | Alexis Schauss | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F1.A5 | 2026-06-01 | Not Started | Evaluate the condition, functionality and safety of the NCDPI building and shared spaces to identify maintenance, modernization and accessibility needs that impact staff and visitor health, safety and productivity. | Derrick Jordan | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F1.A3 | 2026-06-01 | Not Started | Publish and promote an annual collection of effective and innovative practices drawn from local, statewide and national research, to inform policy, NCDPI work and PSU improvement efforts. | Michael Maher |  | Shaun Kellogg |  |  | 2025-12-02 | 2025-12-02 |  | https://docs.google.com/document/d/12Y5iBG19iTSF34PuQ-qjlVZYYJeJ7k1jvvxUusHYMRI/edit?tab=t.0 | 2025-12-02 17:25 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F3.A2 | 2026-06-01 | Not Started | Explore strategies, including how to creatively use currently available funding allotments, to recruit and retain highly effective teachers and principals to work in low-performing schools and districts. | Alexis Schauss | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F1.A1 | 2026-07-01 | Not Started | Expand student recruitment programs starting no later than middle school, including career academy programs, “Teaching as a Profession” CTE pathways and other programs to encourage more students to engage in the education profession. | Derrick Jordan | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F1.A2 | 2026-07-01 | Not Started | Revise and strengthen Beginning Teacher (BT) policy and supports, including exploring a standard statewide definition of BTs and regionalized support approaches with partners. | Derrick Jordan | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F2.A3 | 2026-07-01 | Not Started | Develop a uniform NCDPI model for instructional coaching that integrates literacy, numeracy and supports for low-performing schools. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F4.A1 | 2026-07-01 | Not Started | Engage with local boards of education to honor teachers and principals of the year, expand meaningful advisor roles for teachers and principals at the district and state levels and identify additional ways to publicly recognize educator excellence. | Derrick Jordan | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F2.A3 | 2026-07-01 | Not Started | Engage and align non-education partners' communication efforts for this initiative | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F2.A3 | 2026-08-01 | Not Started | Design a Pre-K–12 Teaching and Learning Framework with PSUs to set shared expectations for standards-aligned instruction, integrated supports and access to high-quality learning for all students. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F3.A2 | 2026-08-01 | Not Started | Expand access to advanced learning opportunities K-12, including NC Governor’s School and K-8 talent development programming, aligned to student strengths, interests and career pathways. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F4.A3 | 2026-08-01 | Not Started | Identify strategies for PSUs to strengthen grade level transitions through coordinated planning, advising and personalized pathways between pre-K, elementary, middle and high school. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F4.A4 | 2026-08-01 | Not Started | Promote whole-child development and student engagement by expanding access to arts, athletics and student-led leadership opportunities that are aligned to academic standards and designed to cultivate students’ strengths, interests and well-being. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F4.A5 | 2026-08-01 | Not Started | Establish scalable approaches to embed artificial intelligence safely, responsibly and ethically, and ensure collaborative problem-solving is included in the learning experience. | Vanessa Wrenn | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F1.A3 | 2026-08-01 | Not Started | Develop, adopt and promote statewide standards for high-quality professional learning to serve as guidance for the design and evaluation of professional learning opportunities, including microcredentials. | Vanessa Wrenn | Derrick Jordan | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F4.A2 | 2026-08-01 | Not Started | Explore models that increase instructional capacity by reducing burden on teachers, including eliminating or significantly reducing unpaid teacher duties, streamlining compliance processes, increasing teacher planning time and increasing flexible scheduling. | Geoff Coltrane | Maria Pitre-Martin | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F2.A4 | 2026-08-01 | Not Started | Develop a student behavior pilot to address behavior challenges and scale trauma-informed practices in PSUs identified with significant discipline referrals. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F2.A5 | 2026-08-01 | Not Started | Support PSUs in implementing Positive Behavioral Interventions and Supports (PBIS) and share best practices for fostering supportive school environments and reducing behavioral challenges. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F1.A6 | 2026-08-01 | Not Started | Review, refine and standardize work order, maintenance and operational support request processes to ensure consistent, timely and transparent service delivery to all NCDPI offices and stakeholders. | Vanessa Wrenn | Derrick Jordan | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F3.A3 | 2026-08-01 | Not Started | Launch enhanced data analytic tools for use with the NCSIS. | Vanessa Wrenn | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F2.A2 | 2026-08-01 | Not Started | Develop toolkits for PSUs to engage families and partners in their schools. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F3.A1 | 2026-08-01 | Not Started | Engage local and state policymakers on attending events, visiting schools and participating in public education initiatives. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F3.A4 | 2026-09-01 | Not Started | Audit agency contracts to identify opportunities for cost savings, increased efficiency and improved return on investment, with special focus on technology-related agreements. | Vanessa Wrenn | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F2.A1 | 2026-09-01 | Not Started | Establish statewide, regional and partner education networks to facilitate implementation of key strategic plan priorities, share scalable resources and support continuous improvement across PSUs. | Maria Pitre-Martin | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F2.A2 | 2026-09-01 | Not Started | Create and maintain shared resources, assets and digital tools for use by education networks, enabling districts and schools to accelerate strategic initiatives and replicate effective practices. | Maria Pitre-Martin | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F3.A3 | 2026-09-01 | Not Started | Adopt statewide protocols, including diagnostics, planning tools and fidelity monitoring to guide local improvement efforts for low-performing schools. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F1.A2 | 2026-09-01 | Not Started | Connect and align NCDPI, education partners and allies to support local, regional and statewide efforts. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F1.A3 | 2026-09-01 | Not Started | Encourage and support aligned initiatives and outreach via social media, media and events. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F3.A2 | 2026-10-01 | Not Started | Engage businesses, individuals and philanthropic organizations to invest in PSUs at the local, regional and state levels. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F3.A1 | 2026-11-01 | Not Started | Advocate to the North Carolina General Assembly, in partnership with educators, business leaders and community leaders, for competitive teacher, principal and other school staff compensation, including pay for advanced degrees. | Geoff Coltrane | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F3.A2 | 2026-11-01 | Not Started | Develop and advocate for a revised principal compensation model with partners that includes increased base pay, factors for school complexity and retention incentives to better attract and keep leaders in the schools that need them most. | Alexis Schauss | Geoff Coltrane | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F4.A3 | 2026-11-01 | Not Started | Explore reforms to North Carolina’s school funding model to ensure allocations are transparent, flexible and based on student needs. | Alexis Schauss | Geoff Coltrane | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F3.A3 | 2026-11-01 | Not Started | Work with partners to advocate for investments in public schools, especially for initiatives for improving student achievement and school infrastructure. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F3.A3 | 2026-12-01 | Not Started | Promote appropriate screening, identification practices and policy shifts that reduce disproportionality in AIG and EC services and expand instructional support for multilingual learners across North Carolina schools. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 16:13 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F4.A4 | 2026-12-01 | Not Started | Publish new School Performance Profiles based on the redesigned accountability system to ensure public transparency and equip communities with clear data on local school success. | Michael Maher | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F3.A4 | 2026-12-01 | Not Started | Create a statewide foundation to fund various initiatives in this and future strategic plans | Rupen Fofaria | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F1.A2 | 2027-01-01 | Not Started | Build on the implementation of North Carolina’s Science of Reading initiative by continuing to expand high- impact literacy practices and launch a parallel focus on foundational mathematics to support early learning. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F3.A4 | 2027-01-01 | Not Started | Explore opportunities to have high school students take an ACT preparation course prior to taking the ACT in the 11th grade. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F4.A6 | 2027-01-01 | Not Started | Provide PSUs with technical assistance to monitor credits toward graduation to support PSUs in keeping students on track for graduation. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F5.A1 | 2027-01-01 | Not Started | Develop a statewide toolkit to support schools in implementing high-quality character education that teaches students to be good citizens and important values, such as respect, responsibility, integrity, perseverance, courage, justice and self-discipline. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F5.A2 | 2027-01-01 | Not Started | Explore ways to expand service learning programs for students to ensure every student has access to service learning opportunities. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F1.A4 | 2027-01-01 | Not Started | Advocate for expanding the teacher pipeline and lowering financial barriers to entering the profession, in partnership with educator preparation programs (EPPs). | Derrick Jordan | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F4.A3 | 2027-01-01 | Not Started | Launch a statewide teacher reverence initiative that highlights educator stories and contributions, trains educators to serve as recruiters of future teachers and partners with local chambers of commerce and community organizations to celebrate and support educators. | Mark Dessauer | Derrick Jordan | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F2.A2 | 2027-01-01 | Not Started | Promote partnerships between PSUs and local community organizations to provide support for families, especially in underserved areas. | Stacey Wilson-Norman (Office of Teaching and Learning) | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F2.A3 | 2027-01-01 | Not Started | Increase NCDPI supports for the educators who serve as a bridge to the local community, such as nurses, counselors, social workers, school psychologists and parent liaisons. | Stacey Wilson-Norman (Office of Teaching and Learning) | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F2.A6 | 2027-01-01 | Not Started | Partner with PSUs for widespread implementation of physical activity recommendations in State Board Policy SHLT-000. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F3.A5 | 2027-01-01 | Not Started | Identify and promote PSU best practices for operational efficiency, such as shared services models, and engage the business community to leverage expertise on operational effectiveness. | Alexis Schauss | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F3.A6 | 2027-01-01 | Not Started | Explore ways to leverage machine learning, artificial intelligence and advanced analytics to enhance NCDPI efficiency and extend value and insights essential to all statewide stakeholders | Vanessa Wrenn | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 7 | P7.F3.A4 | 2027-01-01 | Not Started | Evaluate the initiative’s impact on public school satisfaction, knowledge and perception from families, students and NC residents. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F2.A3 | 2027-01-01 | Not Started | Develop toolkits for local chambers, businesses and community organizations to work with eighth graders on their career development plans and 12th graders on their post-secondary plans. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F1.A3 | 2027-03-01 | Not Started | Encourage PSUs that utilize SROs to ensure all SROs receive training appropriate for working with school- aged children, in collaboration with the Governor’s Advisory Council for Student Safety and Well-Being and local law enforcement agencies. | Stacey Wilson-Norman | Rupen Fofaria | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F1.A5 | 2027-05-01 | Not Started | Create a virtual NCDPI Family Academy that could be linked to PSU websites that will offer accessible, webinar-style learning sessions for families. | Maria Pitre-Martin | Mark Dessauer | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F2.A4 | 2027-05-01 | Not Started | Advocate for evidence-based school models, such as “community schools,” that reduce barriers by promoting community resources to support student and family well-being. | Maria Pitre-Martin | Stacey Wilson-Norman | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 2 | P2.F2.A4 | 2027-07-01 | Not Started | Continue to expand leadership academies in collaboration with state and regional partners for aspiring principals and superintendents, particularly in high-poverty and low-performing schools and provide specialized professional learning for financial officers and charter leaders to strengthen strategic management. | Derrick Jordan | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F5.A3 | 2027-08-01 | Not Started | Develop a system for tracking students’ post-secondary transitions, including to postsecondary education, employment or military service within 12 months of graduation. | Michael Maher | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F2.A3 | 2027-10-01 | Not Started | Convene an annual statewide and interstate networks conference to showcase innovative pre-K–12 practices, host immersive site visits and expand access to research-driven models. | Maria Pitre-Martin | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 3 | P3.F2.A5 | 2027-12-01 | Not Started | Identify and share best practices around partnerships between PSUs and local health professionals for providing mental and physical health supports to students and staff. | Stacey Wilson-Norman | Rupen Fofaria | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F2.A7 | 2027-12-01 | Not Started | Partner with community and health service organizations to identify and share strategies to expand school- based health services for students and staff, including telehealth. | Stacey Wilson-Norman | Rupen Fofaria | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F2.A8 | 2027-12-01 | Not Started | Increase educator capacity to address student mental health needs by expanding Youth and Teen Mental Health First Aid training. | Stacey Wilson-Norman | Rupen Fofaria | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F1.A3 | 2028-01-01 | Not Started | Explore how to increase play-based learning in early childhood classrooms to better foster children’s social, emotional, cognitive and physical development. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F5.A4 | 2028-01-01 | Not Started | Create awards for student service learning projects at the school and district levels, as well as a state- level high school diploma endorsement from NCDPI. | Stacey Wilson-Norman (Office of Teaching and Learning) | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F3.A7 | 2028-01-01 | Not Started | Modernize the financial, human resources and licensure systems across both NCDPI and PSUs. | Alexis Schauss | Vanessa Wrenn | [7 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 6 | P6.F3.A4 | 2028-03-01 | Not Started | Expand SBE and NCDPI efforts to support districts designated as low-performing and districts experiencing financial challenges. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 1 | P1.F5.A5 | 2028-08-01 | Not Started | Create and award durable skills endorsements for graduating students who demonstrate mastery of critical competencies aligned to the Portrait of a Graduate. | Stacey Wilson-Norman (Office of Teaching and Learning) | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 4 | P4.F2.A9 | 2028-08-01 | Not Started | Enhance operational efficiency and maximize allowable Medicaid reimbursements for school-based services across PSUs. | Stacey Wilson-Norman | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 5 | P5.F3.A8 | 2028-08-01 | Not Started | Design, deploy and operationalize a centralized and unified data visualization platform for NCDPI data. | Vanessa Wrenn | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F3.A5 | 2028-11-01 | Not Started | Highlight the changing narrative on public education in North Carolina and how it is part of the state’s identity. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov
Pillar 8 | P8.F3.A6 | 2030-06-01 | Not Started | Work with partners to explore creating an endowment that will allow all public high school graduates, regardless of income, to attend at least two years of postsecondary education completely tuition-free inclusive of federal and state financial aid. | Mark Dessauer | [8 empty] | 2025-11-20 17:34 | geoff.coltrane@dpi.nc.gov